## Sheet1
As A… | I want to… | Because… | Hours | Priority
User/ Administrator | Log in | I want to access my account | 2 | 10
User | Register | I want to create an account | 3 | 10
User | View my profile | I want to see my information | 3 | 10
User | Update my profile | I want to update my information | 4 | 10
User | Delete my profile | I don't want to be a part of the site | 3 | 10
User | Search recipes | I can find the recipe I’m looking for | 6 | 10
User/. Guest | View recipes | I can cook the recipe | 4 | 10 | Sprint 1
Administrator | View all profiles | I can see all the users | 5 | 20
Administrator | Update a profile | I may need to change the content of the profile | 5 | 20
Administrator | Delete a profile | I don't want the user on my site | 5 | 20
Administrator | Update a recipe | I may need to change the content of the recipe | 5 | 20
Gues | Lock out profiles | I don't want a guest to be able to view profiles | 4 | 20
User | Create a recipe | I want to add my recipe to the site | 6 | 30 | Sprint 2
User | Update my recipes | I want to change the content of my recipes | 5 | 30
User | Delete my recipes | I want to remove my recipe from the site | 6 | 30
User | Print recipes out | I want to be able to get a physical copy of a recipe | 6 | 30
User | Review Recipes | I want to leave feedback on a recipe | 6 | 30
User | Comment on a recipe | I want to leave feedback on a recipe | 4 | 30 | Sprint 3